## Deals
Following up on contacts and content (see summary of activities email with pointer to Activities Summary) | Activity/ Milestones | Notes (Concern/ Risks/ Next Steps) | WE 11/22 | WE 11/29 | WE 12/6 | WE 12/11
USCIS Accounts Public Tech Challenge | Prepping in anticipation of code challenge notice | Submitted on 10/21 | no change |  |  | updated
TPVS | Awaitng feedback from prime and/or RFP release, Kelly to reach out to prime |  |  |  |  | updated
NMMES-TR | Conducted three days of Orals preparation and planning sessions in Reston 12/9 -11. | Conduct Orals preparation and planning sessions in Reston 12/16 -18. | Updated | Updated | Updated | Updated
| Conducted Pricing Sessions with Microsoft on 12/10 and 12/11. | Conduct Pink Team Review on 12/18-19. | Updated | Updated | Updated | Updated
| Conducted Pricing Session with Service Now on 12/9. | Finalize pricing for Microsoft and Service Now. | Updated | Updated | Updated | Updated
| Supported Key Personnel (specifically Phil Charles, Chief Engineer, Pedro Cadenas, Cybersecurity Lead Engineer, Marc Hidalgo, Chief Data Scientist/Chief of Data Analytics) in development of slides for oral presentation of System Capability Solution and Technical Approach components of proposal. | Support Key Personnel (specifically Phil Charles, Chief Engineer, Pedro Cadenas, Cybersecurity Lead Engineer, Marc Hidalgo, Chief Data Scientist/Chief of Data Analytics) in development of slides for oral presentation of System Capability Solution and Technical Approach components of proposal. | Updated | Updated | Updated | Updated
USPTO TMX | Following up on contacts and content (see summary of activities email with pointer to Activities Summary), Still alot of different communications about what TMX will look like contractually, DR was Monday wiht approval to proceed | Lots of prep for f2f next week (TH/F) in Alexandria | Updated | updated | updated | updated
USPTO BOSS | Continued prep for meeting w/decisino makers next week - much of ITSM and TMX are groundwork for recompete as well. SUpported Stealth deep dive use case into securing their mainframe ecosystem (TRAM) for TMX, follow up will cover broader BOSS agendas such as DevOps (and CI/CD environments) as well as General Cloud | Latest feedback from USPTO - The technical review is complete on BOSS, and all RFIs have been scored, The team is currently working with procurement on producing the down-selected group Still on track for February release, The government is targeting a minimum of ten awardees, Government is fully expecting a protest on BOSS, The official start of work on BOSS will be sometime in October after protests. If the protest delay the procurement to long, the USPTO is going to start looking at other vehicles | updated | updated | updated | updated
USPTO ITSM/ServiceNow | several meetings and basic slides to prime the meeting with USPTO for this oppotunity (expected 1st quarter).... consistent message from unisys on this importtnt to BOSS | We have extensive REmedy ITSM at USPTO, so leveraging thsi and numerous other integration points to bolster Unisys as ServiceNow best vendor (e.g. as RPA for Stealth i.e. we use it) |  |  |  | updated
DOD DHA | Completed - planned submission Thursday | Edit/Format complete, up front contract content to be added for final submission | updated
USAF DevOps Service | Unisys was selected for the BPA on Industry Day on 11/13 following presentation, vehicle is currently under protest | awaiting potential BPA calls | no change |  |  | updated
COMET FAS CALM | Continue support of DSI as prime partner (still awaiting TA), and review other vendors for gap services. Discussing additional opps to influence given current delay and speculation of possible shifts to "COMET" thinking over independent COTS-oriented procurement | The challenge remains the eval is very "COTS like" (what of the ~1600 entries in RTM can you meet very quickly and wiht no added cost) versus repeated stipulation that no single COTS can meet all requirements... possibly the delay is feedback that htis evaluation will not result in excellent proposals (but that too is speculation) DSI (heart of solution) is missing a couple of key requiremetns in the RTM so that is focus of deep dive... Feedback from Mark FForeman suggests other areas they _should_ be looking at but not clear they are in evaluation criteria... | updated | updated | updated | updated
IWRP OTAS | Attended webinar industry day and evaluated problem statements released this week. | Identify white papers to target and plan responses. Currently working on Speech to Text (105), DHA Legacy Data Consolidation (102), and NMMES Financial System Replacement (111) - All 3 white papers have been submitted | Updated |  |  | updated
DHA MHS Industry Day | Submitted CloudForte focused white paper on 11/8 | Unisys was invited for 1 on 1 discussion with DHA on Industry Day on 11/21 | Updated |  |  | no change
NOAA Cloud Task Order | Submitted
C5 CEMI | Red Team 11/22 | recovery and submission on 11/25 | Updated
USAF AFOSI | Art to investigate with MicroPact when we can get in to see client. | Meeting may not occur until Q1 2020 |  |  | updated
USAF Low Code/No Code | Bryan investigating ServiceNow to evaluate appropriateness of platform for this deal. |  |  |  | updated
OTA DHA Legacy Data | Prepared presentation for 12/16 demo | After 12/16 demo we will be advised on whether we should submit for the RFP |  |  |  | updated
FDIC FFIEC | Held initial technical background session | Will continue with weekly sessions |  |  |  | updated

## Capabilities
Capability Name | Activity/ Milestones | Notes (Concern/ Risks/ Next Steps) | WE 11/22 | WE 12/6
All |  |  | no change
LeanGov 2.0 | Waiting Comments on MM document and Delivery Lifecycle (DevOps), working on reducing size and standard form across blueprints. Suggested opportunities for alignment in group (e.g. Tech Radar could reflect LeanGov taxonomy so they compliment, DOJO training should align wiht previous work for Unisys training/certs in complimentary areas. Getting several requests for inputs across programs.... I need to escalate that we dont have an effective way of communicating content (and show a POC I'm working to propose better promotion and evangelism | Working on POC for better presentation of content, engaging SMEs and programs for feedback (OCM, DevOps, Relational Contracting), may make sense for Sales Kickoff (working on resource request and review).... alignment with Corporate OCM Susan Rudman to promote single story (she is also doing NMMES) | updated | updated | updated
Dojo | Held successful 2 day acceleration program | Tracking toward MVP in December and soft launch at annual Sales Kickoff | Updated
Tech Challenge Readiness | Began baselining (using the Dojo) of core team and harvesting of lessons learned / existing artifacts | next step - Formalize framework and present to SLT | Updated
Low Code / No Code |  | next step - Develop strategy for ServiceNow, followed by Salesforce/MicroPact/others. | no change | Learning Service-Now platform
Cloud Native App Dev | Ongoing development of Capability Definition, Elevator Pitch, and Roadmap development | Finalize Maturity Level 1 artifacts | no change
DataOps | Draft quickpage complete; vendor evaluations ongoing | Finalize Maturity Level 1 artifacts | Updated
Hybrid Integration Platform |  | No updates planned until after NMMES-TR is submitted. | no change
CloudForte | Got all the demonstrations working again, brought DB up to date, created some Quicksite visualizations, created a UCF Landing Zone | Connect UCF LZ to Unisys Fed AD, Establish SSO | updated

## Delivery
Delivery Org | Client | Notes (Milestones/Concerns/ Risks/Next Steps)
CAMCOE | IRS | Health Check - These activities are successfully completed for this year and no major issues or concerns were identified.
| GSA | Data Analytics - Working with MicroStrategy team to identify where to use Dossiers vs. RSDs in the Dashboard/Reports generation for LPT. Mobile Apps - New version of FMS2Go planned for release this weekend. COMET: Working with the Account team to provide intel and assistance with the upcoming PPM and Fleet proposal efforts.
| HUD | Looking into opportunities for Application Modernization activities.
| Staffing | Action initiated for the following for CAMCOE Staff augmentation: 1. To bring in Frank Sweet as a Contractor to work on part-time basis subsequent to his retirement end of Dec-2019. 2. Req opened to find a replacement for Frank. Candidate identified and working with RAP vendor to move forward to bring him on board. 3. Req opened to hire a candidate to support CMplus Administration in IRS. Candidate identified for this. Working with Procurement on this to bring him on board effective 3-Jan-2020.
| Cross-BU | Working with Unisys ClearPath Engineering to identify customer centric Test automation efforts for OS 2200 systems. Meeting being scheduled with the Engineering team and Sales and Account Executives for the IRS, HUD and DISA accounts.
CloudForte | VA | Continue to support Large architecture tasks
| NOAA | Cloud candidate interview support
| CFPB | TAM candidate requisition prep